## 📊 Summary
🧪 SEMANTIC TEST ENGINE — SESSION REPORT
Session: 20260220_232458 ¦ Generated: 2026-02-20 23:29:39
Total Stories | ✅ Passed | ❌ Failed | ⏭ Skipped | Pass Rate
4 | 0 | 0 | 4 | 0%
Story ID | Context Name | Persona | Status | Steps (Pass/Total) | Failure Reason
STORY-001 | Upload and Save Cover Pages | Ministry Admin | ⏭ SKIPPED | 5 / 5 | —
STORY-002 | Cancel Upload Cover Pages | Ministry Admin | ⏭ SKIPPED | 5 / 5 | —
STORY-003 | Upload and Save Profile Picture | Ministry Admin | ⏭ SKIPPED | 5 / 5 | —
STORY-004 | Cancel Upload Profile Picture | Ministry Admin | ⏭ SKIPPED | 5 / 5 | —

## 📋 User Test Stories
📋 USER TEST STORIES
Documents every user scenario tested: persona, context, field values used, execution steps, and pass/fail outcome.
Story ID | Context / Feature | User Persona | Scenario Description | Status | Steps Total | Steps Passed | Pass % | Failure Reason
STORY-001 | Upload and Save Cover Pages | Ministry Admin | The Ministry Admin uploads multiple cover pages and saves the changes to update the ministry profile's visual representation. | ⏭ SKIPPED | 5 | 5 | 100% | —
STORY-002 | Cancel Upload Cover Pages | Ministry Admin | The Ministry Admin initiates the upload of cover pages but cancels the operation to ensure no changes are made to the profile. | ⏭ SKIPPED | 5 | 5 | 100% | —
STORY-003 | Upload and Save Profile Picture | Ministry Admin | The Ministry Admin uploads a new profile picture to update the ministry's visual identity. | ⏭ SKIPPED | 5 | 5 | 100% | —
STORY-004 | Cancel Upload Profile Picture | Ministry Admin | The Ministry Admin initiates the upload of a profile picture but cancels the operation to ensure no changes are made to the profile. | ⏭ SKIPPED | 5 | 5 | 100% | —
FIELD VALUES USED IN EACH STORY
Story ID | Context | Field Name | Value Used | Expected Outcome
STORY-001 | Upload and Save Cover Pages | — | — | Cover pages are uploaded and saved successfully, reflecting changes on the ministry profile. VALIDATION: Assert: Cover pages are visible on the ministry profile. Assert: No error messages are displayed.
STORY-002 | Cancel Upload Cover Pages | — | — | No changes are made to the cover pages on the ministry profile. VALIDATION: Assert: Cover pages remain unchanged. Assert: No new files are uploaded.
STORY-003 | Upload and Save Profile Picture | — | — | Profile picture is uploaded and saved successfully, updating the ministry profile. VALIDATION: Assert: Profile picture is updated on the ministry profile. Assert: No error messages are displayed.
STORY-004 | Cancel Upload Profile Picture | — | — | No changes are made to the profile picture on the ministry profile. VALIDATION: Assert: Profile picture remains unchanged. Assert: No new file is uploaded.
DETAILED EXECUTION STEPS
Story ID | Step # | Action | Target Element | Value Used | Result | Error |  | Timestamp
STORY-001 | 1 | explore | Step 1: Click 'Unggah Beberapa Halaman Sampul' |  | ✅ Pass |  |  | 2026-02-20 23:29:39
STORY-001 | 2 | explore | Step 2: Click 'Browse' to upload files |  | ✅ Pass |  |  | 2026-02-20 23:29:39
STORY-001 | 3 | explore | Step 3: Select files to upload |  | ✅ Pass |  |  | 2026-02-20 23:29:39
STORY-001 | 4 | explore | Step 4: Click 'Simpan & Tutup' |  | ✅ Pass |  |  | 2026-02-20 23:29:39
STORY-001 | 5 | explore | Step 5: Verify cover pages are updated on the profile |  | ✅ Pass |  |  | 2026-02-20 23:29:39
STORY-002 | 1 | explore | Step 1: Click 'Unggah Beberapa Halaman Sampul' |  | ✅ Pass |  |  | 2026-02-20 23:29:39
STORY-002 | 2 | explore | Step 2: Click 'Browse' to upload files |  | ✅ Pass |  |  | 2026-02-20 23:29:39
STORY-002 | 3 | explore | Step 3: Select files to upload |  | ✅ Pass |  |  | 2026-02-20 23:29:39
STORY-002 | 4 | explore | Step 4: Click 'Batal' |  | ✅ Pass |  |  | 2026-02-20 23:29:39
STORY-002 | 5 | explore | Step 5: Verify no changes are made to the cover pages |  | ✅ Pass |  |  | 2026-02-20 23:29:39
STORY-003 | 1 | explore | Step 1: Click 'Unggah Profil' |  | ✅ Pass |  |  | 2026-02-20 23:29:39
STORY-003 | 2 | explore | Step 2: Click 'Browse' to upload a file |  | ✅ Pass |  |  | 2026-02-20 23:29:39
STORY-003 | 3 | explore | Step 3: Select a file to upload |  | ✅ Pass |  |  | 2026-02-20 23:29:39
STORY-003 | 4 | explore | Step 4: Click 'Simpan & Tutup' |  | ✅ Pass |  |  | 2026-02-20 23:29:39
STORY-003 | 5 | explore | Step 5: Verify profile picture is updated on the profile |  | ✅ Pass |  |  | 2026-02-20 23:29:39
STORY-004 | 1 | explore | Step 1: Click 'Unggah Profil' |  | ✅ Pass |  |  | 2026-02-20 23:29:39
STORY-004 | 2 | explore | Step 2: Click 'Browse' to upload a file |  | ✅ Pass |  |  | 2026-02-20 23:29:39
STORY-004 | 3 | explore | Step 3: Select a file to upload |  | ✅ Pass |  |  | 2026-02-20 23:29:39
STORY-004 | 4 | explore | Step 4: Click 'Batal' |  | ✅ Pass |  |  | 2026-02-20 23:29:39
STORY-004 | 5 | explore | Step 5: Verify no changes are made to the profile picture |  | ✅ Pass |  |  | 2026-02-20 23:29:39

## 🔧 Implementation Plan
🔧 IMPLEMENTATION PLAN
Derived from failed stories and identified gaps. Maps each issue to a concrete fix with priority and owner.
# | Feature / Module | Story Reference | Issue Type | Recommended Fix | Priority | Effort | Owner | Status
1 | Test Infrastructure | ALL | Test Coverage | Add negative test cases: invalid email formats, empty required fields, boundary values, special characters. | Medium | L | QA | Open
2 | Auth / Session | ALL | Session Handling | Verify session tokens refresh during long runs. Check auth.json captures all required tokens and cookies. | Low | S | QA | Open
LEGEND: Priority — High = block release ¦ Medium = fix in sprint ¦ Low = nice-to-have Effort — S < 2h ¦ M 2–8h ¦ L > 1 day

## 🚀 Execution Plan
🚀 EXECUTION PLAN
Step-by-step test execution roadmap: what to test, how, with what data, expected outcomes, and who runs it.
EXECUTION PHASES
Phase | Name | Objective | Responsibilities | Duration
Phase 1 | Environment Setup | Verify auth, deploy app, clear test data | QA Lead | 30 min
Phase 2 | Smoke Tests | Run top 3 critical user stories | QA | 1 hr
Phase 3 | Full Story Execution | Run all generated test stories | QA | 2–4 hr
Phase 4 | Regression | Re-run fixed stories from failed set | QA | 1 hr
Phase 5 | Exploratory / Edge | Negative cases, boundary values, edge UX | QA Senior | 2 hr
Phase 6 | Sign-off & Reporting | Review Excel report, raise defects, approve | QA Lead | 30 min
DETAILED EXECUTION STEPS (per Story)
# | Story ID | Feature / Context | Test Steps | Test Data (Key Fields) | Expected Result | Priority | Assigned To | Execution Status
1 | STORY-001 | Upload and Save Cover Pages | 1. EXPLORE 'Step 1: Click 'Unggah Beberapa Halaman Sampul'' 2. EXPLORE 'Step 2: Click 'Browse' to upload files' 3. EXPLORE 'Step 3: Select files to upload' 4. EXPLORE 'Step 4: Click 'Simpan & Tutup'' 5. EXPLORE 'Step 5: Verify cover pages are updated on the profile' |  | Cover pages are uploaded and saved successfully, reflecting changes on the ministry profile. VALIDATION: Assert: Cover pages are visible on the ministry profile. Assert: No error messages are displayed. | Low | QA | ⏭ Pending
2 | STORY-002 | Cancel Upload Cover Pages | 1. EXPLORE 'Step 1: Click 'Unggah Beberapa Halaman Sampul'' 2. EXPLORE 'Step 2: Click 'Browse' to upload files' 3. EXPLORE 'Step 3: Select files to upload' 4. EXPLORE 'Step 4: Click 'Batal'' 5. EXPLORE 'Step 5: Verify no changes are made to the cover pages' |  | No changes are made to the cover pages on the ministry profile. VALIDATION: Assert: Cover pages remain unchanged. Assert: No new files are uploaded. | Low | QA | ⏭ Pending
3 | STORY-003 | Upload and Save Profile Picture | 1. EXPLORE 'Step 1: Click 'Unggah Profil'' 2. EXPLORE 'Step 2: Click 'Browse' to upload a file' 3. EXPLORE 'Step 3: Select a file to upload' 4. EXPLORE 'Step 4: Click 'Simpan & Tutup'' 5. EXPLORE 'Step 5: Verify profile picture is updated on the profile' |  | Profile picture is uploaded and saved successfully, updating the ministry profile. VALIDATION: Assert: Profile picture is updated on the ministry profile. Assert: No error messages are displayed. | Low | QA | ⏭ Pending
4 | STORY-004 | Cancel Upload Profile Picture | 1. EXPLORE 'Step 1: Click 'Unggah Profil'' 2. EXPLORE 'Step 2: Click 'Browse' to upload a file' 3. EXPLORE 'Step 3: Select a file to upload' 4. EXPLORE 'Step 4: Click 'Batal'' 5. EXPLORE 'Step 5: Verify no changes are made to the profile picture' |  | No changes are made to the profile picture on the ministry profile. VALIDATION: Assert: Profile picture remains unchanged. Assert: No new file is uploaded. | Low | QA | ⏭ Pending
PRE-EXECUTION CHECKLIST
✓ | Checklist Item | Responsible
☐ | auth.json is up-to-date with valid tokens | QA Lead
☐ | Target environment URL is correct and accessible | QA
☐ | Test data (users, records) is seeded in environment | Dev / QA
☐ | Browser: Chromium / Chrome latest version | QA
☐ | Screen resolution: 1400×900 (default in test engine) | QA
☐ | Network: application reachable from test machine | Infra
☐ | Logs directory writable (semantic_test_output/) | QA
☐ | Previous test screenshots cleared if re-running | QA