## 📊 Summary
🧪 SEMANTIC TEST ENGINE — SESSION REPORT
Session: 20260224_114717 ¦ Generated: 2026-02-24 11:57:31
Total Stories | ✅ Passed | ❌ Failed | ⏭ Skipped | Pass Rate
4 | 0 | 0 | 4 | 0%
Story ID | Context Name | Persona | Status | Steps (Pass/Total) | Failure Reason
STORY-001 | Edit Role and Save Changes | Super Admin | ⏭ SKIPPED | 8 / 8 | —
STORY-002 | Search for a Role | Super Admin | ⏭ SKIPPED | 3 / 3 | —
STORY-003 | Add New Role | Super Admin | ⏭ SKIPPED | 7 / 7 | —
STORY-004 | Filter Roles by Access Level | Super Admin | ⏭ SKIPPED | 3 / 3 | —

## 📋 User Test Stories
📋 USER TEST STORIES
Documents every user scenario tested: persona, context, field values used, execution steps, and pass/fail outcome.
Story ID | Context / Feature | User Persona | Scenario Description | Status | Steps Total | Steps Passed | Pass % | Failure Reason
STORY-001 | Edit Role and Save Changes | Super Admin | The Super Admin edits the role details for 'Super Admin' and saves the changes to ensure the role information is up-to-date. | ⏭ SKIPPED | 8 | 8 | 100% | —
STORY-002 | Search for a Role | Super Admin | The Super Admin searches for a specific role using the search functionality to quickly locate role information. | ⏭ SKIPPED | 3 | 3 | 100% | —
STORY-003 | Add New Role | Super Admin | The Super Admin adds a new role to the system to expand the role options available for users. | ⏭ SKIPPED | 7 | 7 | 100% | —
STORY-004 | Filter Roles by Access Level | Super Admin | The Super Admin filters the roles by access level to view roles associated with a specific access type. | ⏭ SKIPPED | 3 | 3 | 100% | —
FIELD VALUES USED IN EACH STORY
Story ID | Context | Field Name | Value Used | Expected Outcome
STORY-001 | Edit Role and Save Changes | name | Super Admin | Success toast message appears: 'Data berhasil diperbarui' VALIDATION: Assert: toast message contains 'berhasil'. Assert: modal closes after save
STORY-001 | Edit Role and Save Changes | description | This is a test description
STORY-001 | Edit Role and Save Changes | priorityIndex | 1
STORY-001 | Edit Role and Save Changes | accessId | Ministry
STORY-002 | Search for a Role | Cari | Super Admin | Table refreshes and shows only the role 'Super Admin' VALIDATION: Assert: table row count changes after search. Assert: roleName filter shows 'Super Admin'
STORY-003 | Add New Role | name | New Role | New role appears in the roles table with correct details VALIDATION: Assert: new role 'New Role' is listed in the table with description 'Description for new role'
STORY-003 | Add New Role | description | Description for new role
STORY-003 | Add New Role | priorityIndex | 2
STORY-003 | Add New Role | accessId | Mosque
STORY-004 | Filter Roles by Access Level | accessId | Ministry | Table refreshes and shows only roles with access level 'Ministry' VALIDATION: Assert: table shows only roles with 'Ministry' access level
DETAILED EXECUTION STEPS
Story ID | Step # | Action | Target Element | Value Used | Result | Error |  | Timestamp
STORY-001 | 1 | explore | Step 1: Click 'more_vert' next to 'Super Admin' |  | ✅ Pass |  |  | 2026-02-24 11:57:31
STORY-001 | 2 | explore | Step 2: Click 'Sunting' |  | ✅ Pass |  |  | 2026-02-24 11:57:31
STORY-001 | 3 | explore | Step 3: Fill 'name' with 'Super Admin' |  | ✅ Pass |  |  | 2026-02-24 11:57:31
STORY-001 | 4 | explore | Step 4: Fill 'description' with 'This is a test description' |  | ✅ Pass |  |  | 2026-02-24 11:57:31
STORY-001 | 5 | explore | Step 5: Fill 'priorityIndex' with '1' |  | ✅ Pass |  |  | 2026-02-24 11:57:31
STORY-001 | 6 | explore | Step 6: Select 'accessId' as 'Ministry' |  | ✅ Pass |  |  | 2026-02-24 11:57:31
STORY-001 | 7 | explore | Step 7: Click 'Perbarui' |  | ✅ Pass |  |  | 2026-02-24 11:57:31
STORY-001 | 8 | explore | Step 8: Verify success toast message |  | ✅ Pass |  |  | 2026-02-24 11:57:31
STORY-002 | 1 | explore | Step 1: Fill 'Cari' with 'Super Admin' |  | ✅ Pass |  |  | 2026-02-24 11:57:31
STORY-002 | 2 | explore | Step 2: Press Enter or click search icon |  | ✅ Pass |  |  | 2026-02-24 11:57:31
STORY-002 | 3 | explore | Step 3: Verify table shows only 'Super Admin' role |  | ✅ Pass |  |  | 2026-02-24 11:57:31
STORY-003 | 1 | explore | Step 1: Click 'Tambah' |  | ✅ Pass |  |  | 2026-02-24 11:57:31
STORY-003 | 2 | explore | Step 2: Fill 'name' with 'New Role' |  | ✅ Pass |  |  | 2026-02-24 11:57:31
STORY-003 | 3 | explore | Step 3: Fill 'description' with 'Description for new role' |  | ✅ Pass |  |  | 2026-02-24 11:57:31
STORY-003 | 4 | explore | Step 4: Fill 'priorityIndex' with '2' |  | ✅ Pass |  |  | 2026-02-24 11:57:31
STORY-003 | 5 | explore | Step 5: Select 'accessId' as 'Mosque' |  | ✅ Pass |  |  | 2026-02-24 11:57:31
STORY-003 | 6 | explore | Step 6: Click 'Perbarui' |  | ✅ Pass |  |  | 2026-02-24 11:57:31
STORY-003 | 7 | explore | Step 7: Verify new role appears in table |  | ✅ Pass |  |  | 2026-02-24 11:57:31
STORY-004 | 1 | explore | Step 1: Select 'accessId' as 'Ministry' |  | ✅ Pass |  |  | 2026-02-24 11:57:31
STORY-004 | 2 | explore | Step 2: Click 'Cari' |  | ✅ Pass |  |  | 2026-02-24 11:57:31
STORY-004 | 3 | explore | Step 3: Verify table shows only roles with 'Ministry' access level |  | ✅ Pass |  |  | 2026-02-24 11:57:31

## 🔧 Implementation Plan
🔧 IMPLEMENTATION PLAN
Derived from failed stories and identified gaps. Maps each issue to a concrete fix with priority and owner.
# | Feature / Module | Story Reference | Issue Type | Recommended Fix | Priority | Effort | Owner | Status
1 | Test Infrastructure | ALL | Test Coverage | Add negative test cases: invalid email formats, empty required fields, boundary values, special characters. | Medium | L | QA | Open
2 | Auth / Session | ALL | Session Handling | Verify session tokens refresh during long runs. Check auth.json captures all required tokens and cookies. | Low | S | QA | Open
LEGEND: Priority — High = block release ¦ Medium = fix in sprint ¦ Low = nice-to-have Effort — S < 2h ¦ M 2–8h ¦ L > 1 day

## 🚀 Execution Plan
🚀 EXECUTION PLAN
Step-by-step test execution roadmap: what to test, how, with what data, expected outcomes, and who runs it.
EXECUTION PHASES
Phase | Name | Objective | Responsibilities | Duration
Phase 1 | Environment Setup | Verify auth, deploy app, clear test data | QA Lead | 30 min
Phase 2 | Smoke Tests | Run top 3 critical user stories | QA | 1 hr
Phase 3 | Full Story Execution | Run all generated test stories | QA | 2–4 hr
Phase 4 | Regression | Re-run fixed stories from failed set | QA | 1 hr
Phase 5 | Exploratory / Edge | Negative cases, boundary values, edge UX | QA Senior | 2 hr
Phase 6 | Sign-off & Reporting | Review Excel report, raise defects, approve | QA Lead | 30 min
DETAILED EXECUTION STEPS (per Story)
# | Story ID | Feature / Context | Test Steps | Test Data (Key Fields) | Expected Result | Priority | Assigned To | Execution Status
1 | STORY-001 | Edit Role and Save Changes | 1. EXPLORE 'Step 1: Click 'more_vert' next to 'Super Admin'' 2. EXPLORE 'Step 2: Click 'Sunting'' 3. EXPLORE 'Step 3: Fill 'name' with 'Super Admin'' 4. EXPLORE 'Step 4: Fill 'description' with 'This is a test description'' 5. EXPLORE 'Step 5: Fill 'priorityIndex' with '1'' 6. EXPLORE 'Step 6: Select 'accessId' as 'Ministry'' 7. EXPLORE 'Step 7: Click 'Perbarui'' 8. EXPLORE 'Step 8: Verify success toast message' | name=Super Admin; description=This is a test description; priorityIndex=1; accessId=Ministry | Success toast message appears: 'Data berhasil diperbarui' VALIDATION: Assert: toast message contains 'berhasil'. Assert: modal closes after save | Low | QA | ⏭ Pending
2 | STORY-002 | Search for a Role | 1. EXPLORE 'Step 1: Fill 'Cari' with 'Super Admin'' 2. EXPLORE 'Step 2: Press Enter or click search icon' 3. EXPLORE 'Step 3: Verify table shows only 'Super Admin' role' | Cari=Super Admin | Table refreshes and shows only the role 'Super Admin' VALIDATION: Assert: table row count changes after search. Assert: roleName filter shows 'Super Admin' | Low | QA | ⏭ Pending
3 | STORY-003 | Add New Role | 1. EXPLORE 'Step 1: Click 'Tambah'' 2. EXPLORE 'Step 2: Fill 'name' with 'New Role'' 3. EXPLORE 'Step 3: Fill 'description' with 'Description for new role'' 4. EXPLORE 'Step 4: Fill 'priorityIndex' with '2'' 5. EXPLORE 'Step 5: Select 'accessId' as 'Mosque'' 6. EXPLORE 'Step 6: Click 'Perbarui'' 7. EXPLORE 'Step 7: Verify new role appears in table' | name=New Role; description=Description for new role; priorityIndex=2; accessId=Mosque | New role appears in the roles table with correct details VALIDATION: Assert: new role 'New Role' is listed in the table with description 'Description for new role' | Low | QA | ⏭ Pending
4 | STORY-004 | Filter Roles by Access Level | 1. EXPLORE 'Step 1: Select 'accessId' as 'Ministry'' 2. EXPLORE 'Step 2: Click 'Cari'' 3. EXPLORE 'Step 3: Verify table shows only roles with 'Ministry' access level' | accessId=Ministry | Table refreshes and shows only roles with access level 'Ministry' VALIDATION: Assert: table shows only roles with 'Ministry' access level | Low | QA | ⏭ Pending
PRE-EXECUTION CHECKLIST
✓ | Checklist Item | Responsible
☐ | auth.json is up-to-date with valid tokens | QA Lead
☐ | Target environment URL is correct and accessible | QA
☐ | Test data (users, records) is seeded in environment | Dev / QA
☐ | Browser: Chromium / Chrome latest version | QA
☐ | Screen resolution: 1400×900 (default in test engine) | QA
☐ | Network: application reachable from test machine | Infra
☐ | Logs directory writable (semantic_test_output/) | QA
☐ | Previous test screenshots cleared if re-running | QA