## 📊 Summary
🧪 SEMANTIC TEST ENGINE — SESSION REPORT
Session: 20260224_170546 ¦ Generated: 2026-02-24 17:26:52
Total Stories | ✅ Passed | ❌ Failed | ⏭ Skipped | Pass Rate
5 | 0 | 0 | 5 | 0%
Story ID | Context Name | Persona | Status | Steps (Pass/Total) | Failure Reason
STORY-001 | Search and View Inventory | Mosque Admin searching inventory | ⏭ SKIPPED | 3 / 3 | —
STORY-002 | Add New Stock Entry | Super Admin adding new stock | ⏭ SKIPPED | 10 / 10 | —
STORY-003 | Activate Inventory Item | Mosque Admin managing inventory status | ⏭ SKIPPED | 4 / 4 | —
STORY-004 | Filter and View by Category | Ministry Admin filtering inventory | ⏭ SKIPPED | 3 / 3 | —
STORY-005 | Upload Inventory Document | Super Admin uploading documents | ⏭ SKIPPED | 5 / 5 | —

## 📋 User Test Stories
📋 USER TEST STORIES
Documents every user scenario tested: persona, context, field values used, execution steps, and pass/fail outcome.
Story ID | Context / Feature | User Persona | Scenario Description | Status | Steps Total | Steps Passed | Pass % | Failure Reason
STORY-001 | Search and View Inventory | Mosque Admin searching inventory | The Mosque Admin searches for inventory items using a specific vendor name to view the available stock details. | ⏭ SKIPPED | 3 | 3 | 100% | —
STORY-002 | Add New Stock Entry | Super Admin adding new stock | The Super Admin adds a new stock entry to the inventory system, specifying details such as quantity, purchase price, warranty, and supplier. | ⏭ SKIPPED | 10 | 10 | 100% | —
STORY-003 | Activate Inventory Item | Mosque Admin managing inventory status | The Mosque Admin activates an inactive inventory item to make it available for transactions. | ⏭ SKIPPED | 4 | 4 | 100% | —
STORY-004 | Filter and View by Category | Ministry Admin filtering inventory | The Ministry Admin filters the inventory items by a specific category to view relevant stock details. | ⏭ SKIPPED | 3 | 3 | 100% | —
STORY-005 | Upload Inventory Document | Super Admin uploading documents | The Super Admin uploads a document related to a specific inventory item for record-keeping. | ⏭ SKIPPED | 5 | 5 | 100% | —
FIELD VALUES USED IN EACH STORY
Story ID | Context | Field Name | Value Used | Expected Outcome
STORY-001 | Search and View Inventory | Cari | aifamart | The inventory table updates to show only items supplied by 'aifamart'. VALIDATION: Assert: table row count changes to show only items with 'Nama Vendor' as 'aifamart'.
STORY-002 | Add New Stock Entry | quantity | 100 | A new stock entry is added to the inventory with the specified details. VALIDATION: Assert: new entry appears in the inventory table with 'Nama Produk' as 'Peci' and 'Nama Vendor' as 'aifamart'.
STORY-002 | Add New Stock Entry | purchasePrice | 1000
STORY-002 | Add New Stock Entry | warrentyThru | 19/02/2026, 17:25
STORY-002 | Add New Stock Entry | categoryId | General
STORY-002 | Add New Stock Entry | subCategoryId | General
STORY-002 | Add New Stock Entry | productId | Peci
STORY-002 | Add New Stock Entry | supplierId | aifamart
STORY-003 | Activate Inventory Item | itemStatus | Inactive | The status of the selected inventory item changes to 'Active'. VALIDATION: Assert: status of the item changes to 'Active' in the inventory table.
STORY-004 | Filter and View by Category | categoryId | Perlengkapan Ibadah | The inventory table displays only items under the 'Perlengkapan Ibadah' category. VALIDATION: Assert: table shows only items with 'categoryId' as 'Perlengkapan Ibadah'.
STORY-005 | Upload Inventory Document | file | inventory_document.pdf | The document is successfully uploaded and linked to the inventory item. VALIDATION: Assert: uploaded document appears in the inventory item details.
DETAILED EXECUTION STEPS
Story ID | Step # | Action | Target Element | Value Used | Result | Error |  | Timestamp
STORY-001 | 1 | explore | Step 1: Navigate to Inventaris page |  | ✅ Pass |  |  | 2026-02-24 17:26:52
STORY-001 | 2 | explore | Step 2: Fill Cari with 'aifamart' |  | ✅ Pass |  |  | 2026-02-24 17:26:52
STORY-001 | 3 | explore | Step 3: Verify table updates to show only items from 'aifamart' |  | ✅ Pass |  |  | 2026-02-24 17:26:52
STORY-002 | 1 | explore | Step 1: Click Stok Masuk |  | ✅ Pass |  |  | 2026-02-24 17:26:52
STORY-002 | 2 | explore | Step 2: Fill quantity with '100' |  | ✅ Pass |  |  | 2026-02-24 17:26:52
STORY-002 | 3 | explore | Step 3: Fill purchasePrice with '1000' |  | ✅ Pass |  |  | 2026-02-24 17:26:52
STORY-002 | 4 | explore | Step 4: Fill warrentyThru with '19/02/2026, 17:25' |  | ✅ Pass |  |  | 2026-02-24 17:26:52
STORY-002 | 5 | explore | Step 5: Select categoryId as 'General' |  | ✅ Pass |  |  | 2026-02-24 17:26:52
STORY-002 | 6 | explore | Step 6: Select subCategoryId as 'General' |  | ✅ Pass |  |  | 2026-02-24 17:26:52
STORY-002 | 7 | explore | Step 7: Select productId as 'Peci' |  | ✅ Pass |  |  | 2026-02-24 17:26:52
STORY-002 | 8 | explore | Step 8: Select supplierId as 'aifamart' |  | ✅ Pass |  |  | 2026-02-24 17:26:52
STORY-002 | 9 | explore | Step 9: Click Tambahkan |  | ✅ Pass |  |  | 2026-02-24 17:26:52
STORY-002 | 10 | explore | Step 10: Verify new entry in inventory table |  | ✅ Pass |  |  | 2026-02-24 17:26:52
STORY-003 | 1 | explore | Step 1: Navigate to Inventaris page |  | ✅ Pass |  |  | 2026-02-24 17:26:52
STORY-003 | 2 | explore | Step 2: Click more_vert on an inactive item |  | ✅ Pass |  |  | 2026-02-24 17:26:52
STORY-003 | 3 | explore | Step 3: Click Mengaktifkan |  | ✅ Pass |  |  | 2026-02-24 17:26:52
STORY-003 | 4 | explore | Step 4: Verify status changes to 'Active' |  | ✅ Pass |  |  | 2026-02-24 17:26:52
STORY-004 | 1 | explore | Step 1: Navigate to Inventaris page |  | ✅ Pass |  |  | 2026-02-24 17:26:52
STORY-004 | 2 | explore | Step 2: Select categoryId as 'Perlengkapan Ibadah' |  | ✅ Pass |  |  | 2026-02-24 17:26:52
STORY-004 | 3 | explore | Step 3: Verify table updates to show only relevant items |  | ✅ Pass |  |  | 2026-02-24 17:26:52
STORY-005 | 1 | explore | Step 1: Navigate to Inventaris page |  | ✅ Pass |  |  | 2026-02-24 17:26:52
STORY-005 | 2 | explore | Step 2: Click more_vert on an item |  | ✅ Pass |  |  | 2026-02-24 17:26:52
STORY-005 | 3 | explore | Step 3: Click Upload Document |  | ✅ Pass |  |  | 2026-02-24 17:26:52
STORY-005 | 4 | explore | Step 4: Upload 'inventory_document.pdf' |  | ✅ Pass |  |  | 2026-02-24 17:26:52
STORY-005 | 5 | explore | Step 5: Verify document is linked to item |  | ✅ Pass |  |  | 2026-02-24 17:26:52

## 🔧 Implementation Plan
🔧 IMPLEMENTATION PLAN
Derived from failed stories and identified gaps. Maps each issue to a concrete fix with priority and owner.
# | Feature / Module | Story Reference | Issue Type | Recommended Fix | Priority | Effort | Owner | Status
1 | Test Infrastructure | ALL | Test Coverage | Add negative test cases: invalid email formats, empty required fields, boundary values, special characters. | Medium | L | QA | Open
2 | Auth / Session | ALL | Session Handling | Verify session tokens refresh during long runs. Check auth.json captures all required tokens and cookies. | Low | S | QA | Open
LEGEND: Priority — High = block release ¦ Medium = fix in sprint ¦ Low = nice-to-have Effort — S < 2h ¦ M 2–8h ¦ L > 1 day

## 🚀 Execution Plan
🚀 EXECUTION PLAN
Step-by-step test execution roadmap: what to test, how, with what data, expected outcomes, and who runs it.
EXECUTION PHASES
Phase | Name | Objective | Responsibilities | Duration
Phase 1 | Environment Setup | Verify auth, deploy app, clear test data | QA Lead | 30 min
Phase 2 | Smoke Tests | Run top 3 critical user stories | QA | 1 hr
Phase 3 | Full Story Execution | Run all generated test stories | QA | 2–4 hr
Phase 4 | Regression | Re-run fixed stories from failed set | QA | 1 hr
Phase 5 | Exploratory / Edge | Negative cases, boundary values, edge UX | QA Senior | 2 hr
Phase 6 | Sign-off & Reporting | Review Excel report, raise defects, approve | QA Lead | 30 min
DETAILED EXECUTION STEPS (per Story)
# | Story ID | Feature / Context | Test Steps | Test Data (Key Fields) | Expected Result | Priority | Assigned To | Execution Status
1 | STORY-001 | Search and View Inventory | 1. EXPLORE 'Step 1: Navigate to Inventaris page' 2. EXPLORE 'Step 2: Fill Cari with 'aifamart'' 3. EXPLORE 'Step 3: Verify table updates to show only items from 'aifamart'' | Cari=aifamart | The inventory table updates to show only items supplied by 'aifamart'. VALIDATION: Assert: table row count changes to show only items with 'Nama Vendor' as 'aifamart'. | Low | QA | ⏭ Pending
2 | STORY-002 | Add New Stock Entry | 1. EXPLORE 'Step 1: Click Stok Masuk' 2. EXPLORE 'Step 2: Fill quantity with '100'' 3. EXPLORE 'Step 3: Fill purchasePrice with '1000'' 4. EXPLORE 'Step 4: Fill warrentyThru with '19/02/2026, 17:25'' 5. EXPLORE 'Step 5: Select categoryId as 'General'' 6. EXPLORE 'Step 6: Select subCategoryId as 'General'' 7. EXPLORE 'Step 7: Select productId as 'Peci'' 8. EXPLORE 'Step 8: Select supplierId as 'aifamart'' ... +2 more steps | quantity=100; purchasePrice=1000; warrentyThru=19/02/2026, 17:25; categoryId=General (+3 more) | A new stock entry is added to the inventory with the specified details. VALIDATION: Assert: new entry appears in the inventory table with 'Nama Produk' as 'Peci' and 'Nama Vendor' as 'aifamart'. | Low | QA | ⏭ Pending
3 | STORY-003 | Activate Inventory Item | 1. EXPLORE 'Step 1: Navigate to Inventaris page' 2. EXPLORE 'Step 2: Click more_vert on an inactive item' 3. EXPLORE 'Step 3: Click Mengaktifkan' 4. EXPLORE 'Step 4: Verify status changes to 'Active'' | itemStatus=Inactive | The status of the selected inventory item changes to 'Active'. VALIDATION: Assert: status of the item changes to 'Active' in the inventory table. | Low | QA | ⏭ Pending
4 | STORY-004 | Filter and View by Category | 1. EXPLORE 'Step 1: Navigate to Inventaris page' 2. EXPLORE 'Step 2: Select categoryId as 'Perlengkapan Ibadah'' 3. EXPLORE 'Step 3: Verify table updates to show only relevant items' | categoryId=Perlengkapan Ibadah | The inventory table displays only items under the 'Perlengkapan Ibadah' category. VALIDATION: Assert: table shows only items with 'categoryId' as 'Perlengkapan Ibadah'. | Low | QA | ⏭ Pending
5 | STORY-005 | Upload Inventory Document | 1. EXPLORE 'Step 1: Navigate to Inventaris page' 2. EXPLORE 'Step 2: Click more_vert on an item' 3. EXPLORE 'Step 3: Click Upload Document' 4. EXPLORE 'Step 4: Upload 'inventory_document.pdf'' 5. EXPLORE 'Step 5: Verify document is linked to item' | file=inventory_document.pdf | The document is successfully uploaded and linked to the inventory item. VALIDATION: Assert: uploaded document appears in the inventory item details. | Low | QA | ⏭ Pending
PRE-EXECUTION CHECKLIST
✓ | Checklist Item | Responsible
☐ | auth.json is up-to-date with valid tokens | QA Lead
☐ | Target environment URL is correct and accessible | QA
☐ | Test data (users, records) is seeded in environment | Dev / QA
☐ | Browser: Chromium / Chrome latest version | QA
☐ | Screen resolution: 1400×900 (default in test engine) | QA
☐ | Network: application reachable from test machine | Infra
☐ | Logs directory writable (semantic_test_output/) | QA
☐ | Previous test screenshots cleared if re-running | QA