## 📊 Summary
🧪 SEMANTIC TEST ENGINE — SESSION REPORT
Session: 20260224_193802 ¦ Generated: 2026-02-24 19:51:44
Total Stories | ✅ Passed | ❌ Failed | ⏭ Skipped | Pass Rate
5 | 0 | 0 | 5 | 0%
Story ID | Context Name | Persona | Status | Steps (Pass/Total) | Failure Reason
STORY-001 | Add New Inventory Transaction | Mosque Admin adding new inventory | ⏭ SKIPPED | 10 / 10 | —
STORY-002 | Search and Verify Inventory | Super Admin searching inventory | ⏭ SKIPPED | 3 / 3 | —
STORY-003 | Filter by Category and Subcategory | Mosque Admin filtering inventory | ⏭ SKIPPED | 3 / 3 | —
STORY-004 | Update Inventory Status | Mosque Admin updating inventory status | ⏭ SKIPPED | 3 / 3 | —
STORY-005 | Upload Inventory Document | Mosque Admin uploading documents | ⏭ SKIPPED | 3 / 3 | —

## 📋 User Test Stories
📋 USER TEST STORIES
Documents every user scenario tested: persona, context, field values used, execution steps, and pass/fail outcome.
Story ID | Context / Feature | User Persona | Scenario Description | Status | Steps Total | Steps Passed | Pass % | Failure Reason
STORY-001 | Add New Inventory Transaction | Mosque Admin adding new inventory | The Mosque Admin adds a new inventory transaction to update the stock of a product. This ensures that the inventory system reflects the current stock levels. | ⏭ SKIPPED | 10 | 10 | 100% | —
STORY-002 | Search and Verify Inventory | Super Admin searching inventory | The Super Admin searches for inventory items using the search function to verify the presence and details of specific products. | ⏭ SKIPPED | 3 | 3 | 100% | —
STORY-003 | Filter by Category and Subcategory | Mosque Admin filtering inventory | The Mosque Admin filters inventory items by category and subcategory to manage specific types of products more efficiently. | ⏭ SKIPPED | 3 | 3 | 100% | —
STORY-004 | Update Inventory Status | Mosque Admin updating inventory status | The Mosque Admin changes the status of an inventory item to 'Active' to reflect its availability for use. | ⏭ SKIPPED | 3 | 3 | 100% | —
STORY-005 | Upload Inventory Document | Mosque Admin uploading documents | The Mosque Admin uploads a document related to an inventory transaction to maintain records and compliance. | ⏭ SKIPPED | 3 | 3 | 100% | —
FIELD VALUES USED IN EACH STORY
Story ID | Context | Field Name | Value Used | Expected Outcome
STORY-001 | Add New Inventory Transaction | Cari | aifamart | The inventory table updates to show the new transaction with the correct details and stock levels. VALIDATION: Assert: new row appears in inventory table with product 'Peci' and quantity '100'. Assert: supplier is 'aifamart'.
STORY-001 | Add New Inventory Transaction | quantity | 100
STORY-001 | Add New Inventory Transaction | purchasePrice | 1000
STORY-001 | Add New Inventory Transaction | warrentyThru | 19/02/2026, 17:25
STORY-001 | Add New Inventory Transaction | categoryId | General
STORY-001 | Add New Inventory Transaction | subCategoryId | General
STORY-001 | Add New Inventory Transaction | productId | Peci
STORY-001 | Add New Inventory Transaction | supplierId | aifamart
STORY-002 | Search and Verify Inventory | Cari | aifamart | The inventory table displays only items supplied by 'aifamart'. VALIDATION: Assert: all visible rows in inventory table have 'Nama Vendor' as 'aifamart'.
STORY-003 | Filter by Category and Subcategory | categoryId | Perlengkapan Ibadah | The inventory table displays only items that match the selected category and subcategory. VALIDATION: Assert: table rows match 'categoryId' as 'Perlengkapan Ibadah' and 'subCategoryId' as 'Shalat'.
STORY-003 | Filter by Category and Subcategory | subCategoryId | Shalat
STORY-004 | Update Inventory Status | productId | Sarung Dewasa | The status of the selected inventory item changes to 'Active'. VALIDATION: Assert: status column for 'Sarung Dewasa' shows 'Active'.
STORY-005 | Upload Inventory Document | file | document.pdf | The document uploads successfully and is associated with the correct inventory transaction. VALIDATION: Assert: document appears in the transaction details with correct filename.
DETAILED EXECUTION STEPS
Story ID | Step # | Action | Target Element | Value Used | Result | Error |  | Timestamp
STORY-001 | 1 | explore | Step 1: Click 'Stok Masuk' button |  | ✅ Pass |  |  | 2026-02-24 19:51:44
STORY-001 | 2 | explore | Step 2: Fill 'quantity' with '100' |  | ✅ Pass |  |  | 2026-02-24 19:51:44
STORY-001 | 3 | explore | Step 3: Fill 'purchasePrice' with '1000' |  | ✅ Pass |  |  | 2026-02-24 19:51:44
STORY-001 | 4 | explore | Step 4: Fill 'warrentyThru' with '19/02/2026, 17:25' |  | ✅ Pass |  |  | 2026-02-24 19:51:44
STORY-001 | 5 | explore | Step 5: Select 'categoryId' as 'General' |  | ✅ Pass |  |  | 2026-02-24 19:51:44
STORY-001 | 6 | explore | Step 6: Select 'subCategoryId' as 'General' |  | ✅ Pass |  |  | 2026-02-24 19:51:44
STORY-001 | 7 | explore | Step 7: Select 'productId' as 'Peci' |  | ✅ Pass |  |  | 2026-02-24 19:51:44
STORY-001 | 8 | explore | Step 8: Select 'supplierId' as 'aifamart' |  | ✅ Pass |  |  | 2026-02-24 19:51:44
STORY-001 | 9 | explore | Step 9: Click 'Tambahkan' button |  | ✅ Pass |  |  | 2026-02-24 19:51:44
STORY-001 | 10 | explore | Step 10: Verify inventory table updates with new transaction |  | ✅ Pass |  |  | 2026-02-24 19:51:44
STORY-002 | 1 | explore | Step 1: Fill 'Cari' with 'aifamart' |  | ✅ Pass |  |  | 2026-02-24 19:51:44
STORY-002 | 2 | explore | Step 2: Click 'Cari' button |  | ✅ Pass |  |  | 2026-02-24 19:51:44
STORY-002 | 3 | explore | Step 3: Verify inventory table shows only items from 'aifamart' |  | ✅ Pass |  |  | 2026-02-24 19:51:44
STORY-003 | 1 | explore | Step 1: Select 'categoryId' as 'Perlengkapan Ibadah' |  | ✅ Pass |  |  | 2026-02-24 19:51:44
STORY-003 | 2 | explore | Step 2: Select 'subCategoryId' as 'Shalat' |  | ✅ Pass |  |  | 2026-02-24 19:51:44
STORY-003 | 3 | explore | Step 3: Verify inventory table updates with filtered items |  | ✅ Pass |  |  | 2026-02-24 19:51:44
STORY-004 | 1 | explore | Step 1: Click 'more_vert' next to 'Sarung Dewasa' |  | ✅ Pass |  |  | 2026-02-24 19:51:44
STORY-004 | 2 | explore | Step 2: Click 'Mengaktifkan' |  | ✅ Pass |  |  | 2026-02-24 19:51:44
STORY-004 | 3 | explore | Step 3: Verify status changes to 'Active' |  | ✅ Pass |  |  | 2026-02-24 19:51:44
STORY-005 | 1 | explore | Step 1: Click 'Upload' button |  | ✅ Pass |  |  | 2026-02-24 19:51:44
STORY-005 | 2 | explore | Step 2: Select 'document.pdf' for upload |  | ✅ Pass |  |  | 2026-02-24 19:51:44
STORY-005 | 3 | explore | Step 3: Verify document appears in transaction details |  | ✅ Pass |  |  | 2026-02-24 19:51:44

## 🔧 Implementation Plan
🔧 IMPLEMENTATION PLAN
Derived from failed stories and identified gaps. Maps each issue to a concrete fix with priority and owner.
# | Feature / Module | Story Reference | Issue Type | Recommended Fix | Priority | Effort | Owner | Status
1 | Test Infrastructure | ALL | Test Coverage | Add negative test cases: invalid email formats, empty required fields, boundary values, special characters. | Medium | L | QA | Open
2 | Auth / Session | ALL | Session Handling | Verify session tokens refresh during long runs. Check auth.json captures all required tokens and cookies. | Low | S | QA | Open
LEGEND: Priority — High = block release ¦ Medium = fix in sprint ¦ Low = nice-to-have Effort — S < 2h ¦ M 2–8h ¦ L > 1 day

## 🚀 Execution Plan
🚀 EXECUTION PLAN
Step-by-step test execution roadmap: what to test, how, with what data, expected outcomes, and who runs it.
EXECUTION PHASES
Phase | Name | Objective | Responsibilities | Duration
Phase 1 | Environment Setup | Verify auth, deploy app, clear test data | QA Lead | 30 min
Phase 2 | Smoke Tests | Run top 3 critical user stories | QA | 1 hr
Phase 3 | Full Story Execution | Run all generated test stories | QA | 2–4 hr
Phase 4 | Regression | Re-run fixed stories from failed set | QA | 1 hr
Phase 5 | Exploratory / Edge | Negative cases, boundary values, edge UX | QA Senior | 2 hr
Phase 6 | Sign-off & Reporting | Review Excel report, raise defects, approve | QA Lead | 30 min
DETAILED EXECUTION STEPS (per Story)
# | Story ID | Feature / Context | Test Steps | Test Data (Key Fields) | Expected Result | Priority | Assigned To | Execution Status
1 | STORY-001 | Add New Inventory Transaction | 1. EXPLORE 'Step 1: Click 'Stok Masuk' button' 2. EXPLORE 'Step 2: Fill 'quantity' with '100'' 3. EXPLORE 'Step 3: Fill 'purchasePrice' with '1000'' 4. EXPLORE 'Step 4: Fill 'warrentyThru' with '19/02/2026, 17:25'' 5. EXPLORE 'Step 5: Select 'categoryId' as 'General'' 6. EXPLORE 'Step 6: Select 'subCategoryId' as 'General'' 7. EXPLORE 'Step 7: Select 'productId' as 'Peci'' 8. EXPLORE 'Step 8: Select 'supplierId' as 'aifamart'' ... +2 more steps | Cari=aifamart; quantity=100; purchasePrice=1000; warrentyThru=19/02/2026, 17:25 (+4 more) | The inventory table updates to show the new transaction with the correct details and stock levels. VALIDATION: Assert: new row appears in inventory table with product 'Peci' and quantity '100'. Assert: supplier is 'aifamart'. | Low | QA | ⏭ Pending
2 | STORY-002 | Search and Verify Inventory | 1. EXPLORE 'Step 1: Fill 'Cari' with 'aifamart'' 2. EXPLORE 'Step 2: Click 'Cari' button' 3. EXPLORE 'Step 3: Verify inventory table shows only items from 'aifamart'' | Cari=aifamart | The inventory table displays only items supplied by 'aifamart'. VALIDATION: Assert: all visible rows in inventory table have 'Nama Vendor' as 'aifamart'. | Low | QA | ⏭ Pending
3 | STORY-003 | Filter by Category and Subcategory | 1. EXPLORE 'Step 1: Select 'categoryId' as 'Perlengkapan Ibadah'' 2. EXPLORE 'Step 2: Select 'subCategoryId' as 'Shalat'' 3. EXPLORE 'Step 3: Verify inventory table updates with filtered items' | categoryId=Perlengkapan Ibadah; subCategoryId=Shalat | The inventory table displays only items that match the selected category and subcategory. VALIDATION: Assert: table rows match 'categoryId' as 'Perlengkapan Ibadah' and 'subCategoryId' as 'Shalat'. | Low | QA | ⏭ Pending
4 | STORY-004 | Update Inventory Status | 1. EXPLORE 'Step 1: Click 'more_vert' next to 'Sarung Dewasa'' 2. EXPLORE 'Step 2: Click 'Mengaktifkan'' 3. EXPLORE 'Step 3: Verify status changes to 'Active'' | productId=Sarung Dewasa | The status of the selected inventory item changes to 'Active'. VALIDATION: Assert: status column for 'Sarung Dewasa' shows 'Active'. | Low | QA | ⏭ Pending
5 | STORY-005 | Upload Inventory Document | 1. EXPLORE 'Step 1: Click 'Upload' button' 2. EXPLORE 'Step 2: Select 'document.pdf' for upload' 3. EXPLORE 'Step 3: Verify document appears in transaction details' | file=document.pdf | The document uploads successfully and is associated with the correct inventory transaction. VALIDATION: Assert: document appears in the transaction details with correct filename. | Low | QA | ⏭ Pending
PRE-EXECUTION CHECKLIST
✓ | Checklist Item | Responsible
☐ | auth.json is up-to-date with valid tokens | QA Lead
☐ | Target environment URL is correct and accessible | QA
☐ | Test data (users, records) is seeded in environment | Dev / QA
☐ | Browser: Chromium / Chrome latest version | QA
☐ | Screen resolution: 1400×900 (default in test engine) | QA
☐ | Network: application reachable from test machine | Infra
☐ | Logs directory writable (semantic_test_output/) | QA
☐ | Previous test screenshots cleared if re-running | QA